## Timeline
<ENTER PROJECT NAME HERE> | Download and save a copy of this file.
<ENTER ORGANIZATION NAME HERE>
Please list milestones, tasks, and deliverables on a separate line below, and identify the month it will be completed. Deliverables should be clearly labeled and align with the budget worksheet.
| January | February | March | April | May | June | July | August | September | October | November | December

## Sample Timeline
<PROJECT NAME>
<Organization Name>
Please list milestones, tasks, and deliverables on a separate line below. Clearly label deliverables.
| January | February | March | April | May | June | July | August | September | October | November | December
Project Start Date | bar: May
Presentation of project concept to Board | bar: May
TASK 1: Develop specific needs / sources / overarching strategy | bar: June
TASK 2: Creative concept development (Design look / color pallet / fonts) | bar: June
DELIVERABLE 1: Do CO Right campaign assets | bar: August
Present first draft to Board | bar: August
TASK 3: Web/digital development starts w/assets developed | bar: September
Updates/review & first look of digital piece to Board | bar: October
DELIVERABLE 2: Signage | bar: November
TASK 4: Order signage / signage production | bar: November
Final edits from Board | bar: January
DELIVERALBE 3: Print or digital | bar: February
TASK 5: Final print files due to printer | bar: February
Print and bindery | bar: February
Project End Date | bar: March

## CTO Use ONLY
<Project Name>
<Organization Name>
| CTO Asset | CTO Review | January | February | March | April | May | June | July | August | September | October | November | December